## Main Project Tasks
Main Tasks
| Percent Over/Under to Flag: | 25%
Project | Category | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Identifiy User requirements from the business scenario and specefication | User Requirements | 2018-04-15 | 2018-04-16 | 7 | 1 | 2018-02-08 |  | 1 | 300
Create Wire frames for HTML pages identified from the user specification | Architectural Design | 2018-04-16 | 2018-04-21 | 60 | 5
Identify software components and technologies used for various parts of the site. E.G. SQL lite database to hold users. PHP to handle web forms etc. | Software Requirements | 2018-04-22 | 2018-04-23 | 5 | 1
Create responsive web page for users to submit a walk | Detailed Design | 2018-04-26 | 2018-05-01 | 70 | 5 | 2018-03-04 | 2018-04-07 | 1 | 390 | 1 | 33
Create PHP script to test submission of a walk as a user | Implementation Unit testing | 2018-05-01 | 2018-05-05 | 50 | 4 | 2018-01-04 | 2018-03-18 | 1 | 500 | 1 | 74
Produce report on what is required for Authentication and authorisation on the website. | Detailed Design | 2018-05-06 | 2018-05-08 | 15 | 2
Produce report on the purpose of version control software. Why it should be used and how it should be used. | Software Requirements | 2018-05-09 | 2018-05-11 | 20 | 2
Test overall site works as it should. Meeting the user specefications. | Integration and system testing | 2018-05-12 | 2018-05-13 | 4 | 1 | 2018-01-14 | 2018-02-02 | 1 | 276 | 1 | 18
Create Acceptance tests to veriy site functionality. Tests should describe requirements, instructions to user, expected outcomes from good data as well as unexpected outcomes from bad data | Integration and system testing | 2018-05-13 | 2018-05-18 | 80 | 5 | 2018-01-14 | 2018-03-01 | 1 | 310 | 1 | 47
Final testing to catch any missed bugs / implement missing features | Operation and mainteneance | 2018-05-20 | 2018-05-20 | 5 | 0 | 2018-02-13 | 2018-02-28 | 1 | 510 |  | 15
Work Plan Reflection | Work plan reflection | 2018-05-20 | 2018-05-22 | 20 | 2 | 2018-03-01 | 2018-03-30 | 1 | 790 | 1 | 29
SETUP

## Project Activities Breakdown
Activities Breakdown
|  | Percent Over/Under to Flag: | 25%
Main Activities | Sub Activities | Category | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Main Task - Identifiy User requirements from the business scenario and specefication |  | User Requirements | 2018-04-12 | 2018-04-12 | 3 | 0 | 2018-02-08
| 1. Which devices should web page work on ( Laptop / Mobile / Desktop) | User Requirements | 2018-04-12 | 2018-04-12 | 1 | 0 | [6 empty] | Needs to work on a Desktop and a mobile device with a width of 400px
| 2. Should be accessible to anybody including those with disabilities | User Requirements | 2018-04-12 | 2018-04-12 | 1 | 0 | [6 empty] | Ensure Colour scheme and accessibiity options such as image text is used.
| 3. Styling should be consisitent across pages | User Requirements | 2018-04-12 | 2018-04-12 | 2 | 0
| 4. Users must be able to submit a walk, which is stored in the database and can be displayed later. | User Requirements | 2018-04-12 | 2018-04-12 | 1 | 0 | 2018-03-04
| 5. Users must be able to submit a review of a walk. | User Requirements | 2018-04-12 | 2018-04-12 | 1 | 0 | 2018-01-04 | [5 empty] | Walk
Main Task - Create Wire frames for HTML pages identified from the user specification |  | Architectural Design | 2018-04-13 | 2018-04-14 | 5 | 1
| 1. Create wireframe for member Registration page | Architectural Design | 2018-04-13 | 2018-04-14 | 6 | 1 | 2018-01-14
| 2. Create wireframe Submitting a walk page. | Architectural Design | 2018-04-13 | 2018-04-14 | 1.5 | 1 | 2018-01-14 | [5 empty] | Submitting a Walk form should include: -Name of Walk -Date -StartTime - Leader - Meeting Point( Lattitude and Longtitude) - Distance in Miles - Route description - notes Status(Proposed/Approved/Rejected
| 3. Create wireframe for Viewing Events page | Architectural Design | 2018-04-13 | 2018-04-14 | 2 | 1 | 2018-02-13
| 4. Create wireframe for Submitting a review page | Architectural Design | 2018-04-13 | 2018-04-14 | 2 | 1 | 2018-02-28
Main Task - Identify Software Components to use |  | Software Requirements | 2018-04-12 | 2018-04-14 | 1 | 2 | 2016-03-05 | [5 empty] | Use provided SQLlite Database. PHP / HTML / CSS / Javascript
Main Task - Produce report on what is required for Authentication and Authorisation |  | Detailed Design | 2018-05-06 | 2018-05-08 | 15 | 2 | [6 empty] | (300 words)
Main Task - Create a responsive web page for users to submit a walk |  | Detailed Design | 2018-04-14 | 2018-04-14 | 70 | 0
| 1. Should be a reflection of the wireframe created earlier | Detailed Design | 2018-04-14 | 2018-04-14 | 63 | 0
| 2. CSS Styling should be suitable | Detailed Design | 2018-04-14 | 2018-04-14 | 20 | 0
| 3. Should work and submit to the TT284 reflector | Detailed Design | 2018-04-14 | 2018-04-17 | 2 | 3
| 4. Include a hidden field to track current user | Detailed Design | 2018-04-14 | 2018-04-14 | 1 | 0 | [6 empty] | field Name: Session ID containing: ABCDEF012345
| 5. Use Media queries to make it suitable for mobile, laptop, desktop | Detailed Design | 2018-04-14 | 2018-04-16 | 15 | 2 | [6 empty] | 400px width for mobile devices
| 6. Form data should be validated by HTML5 | Detailed Design | 2018-04-14 | 2018-04-18 | 15 | 4
| 7. HTML/CSS code should be verified | Detailed Design | 2018-04-14 | 2018-04-18 | 10 | 4 | [6 empty] | https://validator.w3.org/ https://jigsaw.w3.org/css-validator/
Main Task - Create PHP script to test submission of a walk by a user |  | Implementation Unit testing | 2018-05-01 | 2018-05-05 | 50 | 4
| 1. Create a PHP test script which submits a walk and stores the data in the database. | Implementation Unit testing | 2018-05-01 | 2018-05-03 | 20 | 2
| 2. Create a PHP script that will query the database for all walks over a number of days. Past and future. Numbers should entered by the User and validated. | Implementation Unit testing | 2018-05-03 | 2018-05-04 | 20 | 1
| 3. Information about each walk should be presented back to the user in a web page format. | Implementation Unit testing | 2018-05-05 | 2018-05-06 | 10 | 1 | [6 empty] | Styled the same as the submit a walk page.
Main Activity - Test webpages work overall as intended. |  | Integration and system testing | 2018-05-12 | 2018-05-13 | 5 | 1
Main Activity - Acceptance testing - Produce scripted tests for users to document how they should test the site. |  | Integration and system testing | 2018-05-13 | 2018-05-18 | 80 | 5
| 1. Describe requirements the user needs to provide | Integration and system testing | 2018-05-13 | 2018-05-14 | 30 | 1
| 2. Document instructions for user to follow | Integration and system testing | 2018-05-15 | 2018-05-16 | 30 | 1
| 3. Document expected outcomes from good and bad data | Integration and system testing | 2018-05-18 | 2018-05-18 | 20 | 0
Main Activity - Produce a report on version control software and how and why it should be used. |  | Software Requirements | 2018-05-18 | 2018-05-20 | 20 | 2
| 1. Create Local SVN Repo | Software Requirements | 2018-04-12 | 2018-04-13 | 1 | 1
| 2. Show evidence of commit logs. | Software Requirements | 2018-04-12 | 2018-04-18 | 1 | 6 | [6 empty] | Supply two pieces of eveidence. One taken halfway through project. Another taken at the end. Caption evidence to explain what it is.
Main Task - Final check over fro any missed requirements or to fix any bugs found |  | Operation and mainteneance | 2018-05-20 | 2018-05-21 | 5 | 1
Main Task - Work Plan reflection, assesment of effectiveness of planning |  | Work plan reflections | 2018-05-20 | 2018-05-22 | 25 | 2
| 1. Explain what aspectsof the plan were most useful | Work plan reflections | 2018-05-20 | 2018-05-21 | 5 | 1
| 2. Was the risk Assessment useful? | Work plan reflections | 2018-05-20 | 2018-05-21 | 5 | 1
| 3. Did the planning help with completing the EMA? | Work plan reflections | 2018-05-21 | 2018-05-22 | 5
| 4. How would you approach the planning in the future? | Work plan reflections | 2018-05-21 | 2018-05-22 | 5 | 1
| 5. Lessons Learn't | Work plan reflections | 2018-05-21 | 2018-05-22 | 5 | 1
SETUP

## Setup
Setup
Category Name
User Requirements
Software Requirements
Architectural Design
Detailed Design
Implementation Unit testing
Integration and system testing
Work plan reflection
Operation and mainteneance
PROJECTS