## Main Project Tasks
Main Tasks
| Percent Over/Under to Flag: | 25%
Project | Category | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Identifiy User requirements from the business scenario and specefication | User Requirements | 2018-04-07 | 2018-04-08 | 7 | 1 | 2018-01-31 |  | 1 | 300
Create Wire frames for HTML pages identified from the user specification | Architectural Design | 2018-04-08 | 2018-04-13 | 60 | 5
Identify software components and technologies used for various parts of the site. E.G. SQL lite database to hold users. PHP to handle web forms etc. | Software Requirements | 2018-04-14 | 2018-04-15 | 5 | 1
Produce report on what is required for Authentication and authorisation on the website. | Detailed Design | 2018-04-15 | 2018-04-17 | 15 | 2
Create responsive web page for users to submit a walk | Detailed Design | 2018-04-18 | 2018-04-23 | 70 | 5 | 2018-02-24 | 2018-03-30 | 1 | 390 | 1 | 36
Create PHP script to test submission of a walk as a user | Implementation Unit testing | 2018-04-23 | 2018-04-27 | 50 | 4 | 2017-12-27 | 2018-03-10 | 1 | 500 | 1 | 73
Produce report on the purpose of verion control software. Why it should be used and how it should be used. | Software Requirements | 2018-04-28 | 2018-04-29 | 10 | 1
Test overall site works as it should. Meeting the user specefications. | Integration and system testing | 2018-04-30 | 2018-05-02 | 15 | 2 | 2018-01-06 | 2018-01-25 | 1 | 276 | 1 | 19
Create Acceptance tests to veriy site functionality. Tests should describe requirements, instructions to user, expected outcomes from good data as well as unexpected outcomes from bad data | Integration and system testing | 2018-05-03 | 2018-05-08 | 80 | 5 | 2018-01-06 | 2018-02-21 | 1 | 310 | 1 | 45
Final testing to catch any missed bugs / implement missing features | Operation and mainteneance | 2018-05-09 | 2018-05-10 | 24 | 1 | 2018-02-05 | 2018-02-20 | 1 | 510 | 1 | 15
Work Plan Refelction | Category 5 | 2018-02-21 | 2018-03-17 | 750 | 26 | 2018-02-21 | 2018-03-22 | 0 | 790 | 0 | 31
SETUP

## Project Activities Breakdown
Activities Breakdown
| Percent Over/Under to Flag: | 25%
Project Activity | Category | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag icon for Over/Under Actual Work (in hours) | Actual Work (in hours) | Flag icon for Over/Under Actual Duration (in days) | Actual Duration (in days) | Notes
Main Task - Identifiy User requirements from the business scenario and specefication | User Requirements |  |  | 7 |  | 2018-01-31 |  | 1 | 300
1. Which devices should web page work on ( Laptop / Mobile / Desktop) | User Requirements |  |  | 60 | [7 empty] | Needs to work on a Desktop and a mobile device with a width of 400px
2. Should be accessible to anybody including those with disabilities | User Requirements |  |  | 5 | [7 empty] | Ensure Colour scheme and accessibiity options such as image text is used.
3. Styling should be consisitent across pages | User Requirements |  |  | 15
4. Users must be able to submit a walk, which is stored in the database and can be displayed later. |  |  |  | 70 |  | 2018-02-24 | 2018-03-30 | 1 | 390 |  | 36
5. Users must be able to submit a review of a walk. |  |  |  | 50 |  | 2017-12-27 | 2018-03-10 | 1 | 500 |  | 73 | Walk
Main Task - Create Wire frames for HTML pages identified from the user specification |  |  |  | 10
1. Create wireframe for member Registration page | Architectural Design |  |  | 15 |  | 2018-01-06 | 2018-01-25 | 1 | 276 |  | 19
2. Create wireframe Submitting a walk page. | Architectural Design |  |  | 80 |  | 2018-01-06 | 2018-02-21 | 1 | 310 |  | 45 | Submitting a Walk form should include: -Name of Walk -Date -StartTime - Leader - Meeting Point( Lattitude and Longtitude) - Distance in Miles - Route description - notes Status(Proposed/Approved/Rejected
3. Create wireframe for Viewing Events page | Architectural Design |  |  | 24 |  | 2018-02-05 | 2018-02-20 | 1 | 510 |  | 15
4. Create wireframe for Submitting a review page | Architectural Design |  |  | 450 |  | 2018-02-20 | 2018-04-01 | 0 | 430 |  | 41
Main Task - Identify Software Components to use | Software Requirements |  |  | 250 |  | 2016-03-05 | 2016-05-05 | 0 | 200 |  | 60 | Use provided SQLlite Database. PHP / HTML / CSS / Javascript
Main Task - Produce report on what is required for Authentication and Authorisation | Detailed Design | [10 empty] | (300 words)
Main Task - Create a responsive web page for users to submit a walk | Detailed Design
1. Should be a reflection of the wireframe created earlier | Detailed Design
2. CSS Styling should be suitable | Detailed Design
3. Should work and submit to the TT284 reflector | Detailed Design
4. Include a hidden field to track current user | Detailed Design | [10 empty] | field Name: Session ID containing: ABCDEF012345
5. Use Media queries to make it suitable for mobile, laptop, desktop | Detailed Design | [10 empty] | 400px width for mobile devices
6. Form data should be validated by HTML5 | Detailed Design
7. HTML/CSS code should be verified | Detailed Design | [10 empty] | https://validator.w3.org/ https://jigsaw.w3.org/css-validator/
Main Task - Create PHP script to test submission of a walk by a user | Implementation Unit testing
Main Task - Produce report on what is required for Authentication and Authorisation | Detailed Design | [10 empty] | (300 words)
SETUP

## Setup
Setup
Category Name
User Requirements
Software Requirements
Architectural Design
Detailed Design
Implementation Unit testing
Integration and system testing
Operation and mainteneance
PROJECTS