## Sheet1
Event | Likelihood | Impact | Mitigation
Submisison deadline overlaps with another module. If I fall behind on the assignment for the other module it could cause problems. | 2 | I would have to spend time working on the other assignment and risk not having enough time to complete the EMA to the best of my ability | I have already started working on the Assigment for the other module to attempt to get this finished early.
Further research and revision will likely be required in order to complete. The tasks in the EMA. | 4 | Revisiting prior materials and possibly learning new techniques is time consuming. This will eat into my scheduled time to complete the EMA | By working on the project as much as possible and by getting the activities plan completed ASAP I hope to be able to give myself maximum time to complete the EMA.
Working full time with an increasing workload causing more stress and less time to dedicate to study. | 3 | If a sudden increase in work load or new task is given to me to be competed it could cause me to get behind on study due to less time available. | As I work alternating shift pattern. When working nights I can usually fit some time in to study during working hours. This should hopefully aid in my ability to complete the EMA
Social live getting in the way of study time. | 1 | Social live could possibly eat in to study time. Usually social activities have to be planned in advance as all parties are quite busy. It may be that an activity is planned at a crucial moment in the EMA. | Make sure that any planned social activities are thought out in advance and will not leave me lacking time to get the EMA complete. Sacrificing social time if need be.
Hardware failure | 2 | If my primary work laptop develops a fault it could cause time to be lost that could be spent on the EMA. | My EMA files are backed up via dropbox, and also on Github. So if a failure was to occur I could access my files easily. Also I could utilise my company Macbook if I need to.
Illness | 1 | If I become ill this could greatly impact on my ability to complete the EMA | Not a great deal can be done to prevent this. However, I do take a vitamin supplement daily which should help.